## B2B
Bug Id | Module | Sub Module | Bug | Bug Type | Screencast | QA comment | QA Sign-Off | Manager Sign-Off | UAT Deployment | Client Sign-off | Other comments by Client
Bug_01 | Home/Landing Page | Banner | Images contents are not fully visible. It is cutting from up and bottom of the slide | UI | https://prnt.sc/C5ppEkkHM2b4 | Not required. This is actual image size
Bug_02 | Home/Landing Page | Categories>Information page | Download and contact is showing different font family | UI | https://prnt.sc/Aw5CkpPZxW8d | NA
Bug_03 | Home/Landing Page | Categories>Information page | Unable to download the pdf file | Functional | https://www.screencast.com/t/Hb5Vu3pg3 | Need to Discuss with client
Bug_04 | Home/Landing Page | Categories>Information page | Brands are not redirecting on any page. If these are not clickable required. Remove the hyperlinks | Functional | https://www.screencast.com/t/0I0FO8ipGD7 | Fixed
Bug_05 | Home/Landing Page | INSPIRING CULINARY CRAFTSMANSHIP> Read More | Logo size is different. Make it consistant | UI | https://www.screencast.com/t/vKtRUyoSUEJ | Not required.
Bug_06 | Home/Landing Page | INSPIRING CULINARY CRAFTSMANSHIP> Read More | Unnecessary spacing is available on bottom of the restaurant and Hotel page. | UI | https://prnt.sc/4YaStIfqKR0q | Not required.
Bug_07 | Home/Landing Page | Our Brands | Need to center align the text | UI | https://prnt.sc/2XNWR5NYsX9p | Implemented
Bug_08 | Home/Landing Page | Our Brands | Bottom border lines are missing | UI | https://prnt.sc/cfmFDgGCQx81 | Working
Bug_09 | Home/Landing Page | Our Brands | Sometimes last brand is not showing right sided border line | UI | https://prnt.sc/Dts3XC8_V3j3 | Pending
Bug_10 | Home/Landing Page | Our Brands | Hovering on brand is showing "show product brand by <brandname>" but clicking on link, redirect on our brands page. There is no product available. | UI | https://prnt.sc/n7ct5WyobzpG | Remove text
Bug_11 | Home/Landing Page | Our Brands | If all the brands links are redirecting on same page then please remove the clickable action here. Because user will hope these all links will redirect on separate pages. | Functional | https://www.screencast.com/t/0Ihm1y9l | Fixed
Bug_12 | About Us | Who we are | Reduce the space above the content | UI | https://prnt.sc/PDcsXUZRO2ME | NA
Bug_13 | About Us | Who we are | While hover on some location, it is showing the proper details about and other locations are not showing any data | UI | https://www.screencast.com/t/HRutKMcZIf | Need address details from client
Bug_14 | About Us | Services | Show the cross icon on zoom images | UI | https://prnt.sc/-gcBueS1uN9g | Fixed
Bug_15 | About Us | Services | Click control should be on whole the email box. Similar like on Career page | UI | https://www.screencast.com/t/7c612Fok | Fixed
Bug_16 | About Us | Services | Clicking on banner images, redirect to mid of the section. It should redirect to starting of the section | Functional | https://www.screencast.com/t/RFNfzOlnme | Fixed
Bug_17 | Ecatelogues |  | When user submit the form, it should show the message and hide the form. | Functional | https://www.screencast.com/t/wOi1epXc | Pending/ few of tabs are throwing internal error after submit the form
Bug_18 | Ecatelogues |  | When form is opened, only show the single scroll | UI | https://prnt.sc/0tMj7rDxjhDk | Submit button is not visible when validation message is showing
Bug_19 | Ecatelogues | Mobile device | Remove the internal scroll in the pop-up. Instead of this, increase the size of the pop-up | UI | https://prnt.sc/Y4Q2OKE2UqjD | Fixed
Bug_20 | Our brands |  | Links are showing error messages | Functional | https://www.screencast.com/t/BlMu9I90fwO | Pending
Bug_21 | Our brands |  | Reduce the space bottom of the page | UI | https://prnt.sc/4V_cr2VnCaod | Fixed
Bug_22 | Our brands |  | Logos are clickable but not redirecting on any page | Functional | https://www.screencast.com/t/AjVKN7ROtFmH | Fixed
Bug_23 | News and Events | Detail page | Back button should be left aligned. So it would easly visible to user because some times user will ignore on right side | UI | https://prnt.sc/iWQtvzQZu1RT | NA
Bug_24 | News and Events | Detail page | Reduce the spacing between Contact and textbox | UI | https://prnt.sc/J4GS-keXT176 | Fixed
Bug_25 | News and Events | Detail page | Validation is not working on contact form | Functional | https://www.screencast.com/t/rToDwole | Validation is working now but page control is not showing properly on comment section if user blank submit the comment'
Bug_26 | News and Events | Detail page | New added comment is not showing | Functional | https://www.screencast.com/t/lGIb2zZ5Fg3 | Fixed but control of the page should not move to top of the pafe
Bug_27 | News and Events | Detail page (URL- http://chef-b2b.test.tglserver.net/7-delicious-ways-to-use-martins-potato-rolls) | Form inbetween the page is not looking good. Please align this | UI | https://www.screencast.com/t/zyaXy2s6tzGa | NA
Bug_28 | News and Events | Detail page (URL- http://chef-b2b.test.tglserver.net/7-delicious-ways-to-use-martins-potato-rolls) | Redirect to me on other page When I am trying to submit the form blank or with data. | Functional | https://www.screencast.com/t/4kV5GSovyXq | Pending
Bug_29 | News and Events | Detail page | Different font family is used | UI | https://prnt.sc/xAUst9kT2dS0 | Fixed
Bug_30 | News and Events | Detail page (URL- http://chef-b2b.test.tglserver.net/7-delicious-ways-to-use-martins-potato-rolls) | Form fields should be non boldable | UI | https://prnt.sc/kJyIYWZi0Nuc | NA
Bug_31 | Footer |  | Email id should be clickable like all over the application | Functional | https://prnt.sc/VoYgLYjLpR6s | Fixed
Bug_32 | Home>Categories | Asian | "Contact our team for all your Asian ingredients requirements." content show in next line | UI | https://prnt.sc/B9VIsuQepoYb | Fixed
Bug_33 |  | Meet and Poultry | View button is showing anchor tag | UI | https://prnt.sc/GM5IjOoMdc77 | Fixed
Bug_34 |  | Pastry and Bakery | While hovering on Pastry and Bakery is showing only Title Pastry | UI | https://prnt.sc/GM5IjOoMdc78 | Fixed
Bug_35 |  | Pastry and Bakery | Different content used on details page | UI | https://prnt.sc/GM5IjOoMdc79 | Fixed
Bug_36 |  | Dairy | Wrong content is showing on details page | UI | https://prnt.sc/GM5IjOoMdc80 | Fixed
Bug_37 |  | Dairy | As per the sequence of the logo "Danscorella" should show bottom of the page | UI | https://prnt.sc/GM5IjOoMdc81 | as per discussion ,In client mail they ask to reorder the categories in albhabetic order.

## B2C
Bug Id | Module | Sub Module | Bug | Bug Type | Screencast | QA comment | QA Sign-Off | Manager Sign-Off | UAT Deployment | Client Sign-off | Other comments by Client | Developer comment
Bug_01 | Home/Landing Page | Banner | Banner links are throwing the error. | Functional | https://www.screencast.com/t/DLzfCLjtii | Fixed. Now links are not clickable
Bug_03 |  | Recipe | Recipes are using carousel. But there is no left/right arrow or dot in the bottom to know the user. There are more recipes are available to view. | Functional | https://www.screencast.com/t/LN5CvdYBgWW | Fixed
Bug_04 |  | Categories | Reduce the space bottom of the section. | UI | https://prnt.sc/YGwyQHbfeX2- | Fixed
Bug_05 |  | Mobile Device | Recipe and categories are using the carousel. But there are no arrow or anything to know the user that there are more data available. | UI |  | Fixed
Bug_06 | About Us | Mobile Device | This is showing only play icon on the screen. Whole video box is not visible till user click on the video. | UI | https://prnt.sc/7X_RLZ1YIJlx | Not Done
Bug_07 | Recipe | View | Unnecessary blank space is available. | UI | https://prnt.sc/J_m8AiL-_vmj | Fixed
Bug_08 |  | View | Remove the line above the Tips content. | UI | https://prnt.sc/LA2xjvwom1DP | Fixed
Bug_09 |  | View | Resource string missing if user try to add the product in the cart where no product available | Functional | https://prnt.sc/r18Ymmdemrc0 | Fixed.
Bug_10 |  | View | Need to fix the alignment of cooking(both web and mobile) | UI | https://prnt.sc/0CEskbF5fj2F | Fixed.
Bug_11 |  | View | On Mobile device, left/right arrows are cutting from corners on related products section | UI | https://prnt.sc/Dv3mmLTSmETU | Fixed.
Bug_12 | Contact Us |  | Validation message need to be left aligned | UI | https://prnt.sc/FfoLQlUic5hK | Not required
Bug_13 |  |  | When user submit the contact us form, it should not hide the form instead of this, it should show the submit message above the contact us form. | UI | https://prnt.sc/VWUXa88rRSU2 | Not required
Bug_14 |  |  | After submit the form, I refreshed the page and it is showing the previous filled data in the form. | Functional | https://www.screencast.com/t/kxcMGZoasE1 | Fixed
Bug_15 | Register |  | Password required validation is in bold form. | UI | https://prnt.sc/wO3ZkQ0SpxV9 | Fixed
Bug_16 |  |  | When validation messages are showing, view icon alignment got disturbed. | UI | https://www.screencast.com/t/8xY55rcJXoq4 | Not fixed
Bug_17 |  |  | Suggestion- Need to left aligned the validation messages. | UI | https://prnt.sc/48WSd9denTOO | Not required
Bug_18 |  |  | Fix the alignment of password rules. | UI | https://prnt.sc/95NDA0YgfqpA | Fixed
Bug_19 |  |  | Delivery Address is showing what I entered first time and again I change the same that changes are not reflecting. | Functional | https://www.screencast.com/t/fBnbVhqVs | Fixed
Bug_20 |  | Mobile Device | Your Contact Information background width need to increase like other section. | UI | https://prnt.sc/80Ax3hoc-fh8 | Not fixed
Bug_21 |  | Mobile Device | DOB few fields are not visible. | UI | https://prnt.sc/gJWE0h33MQan | Fixed
Bug_22 |  | Mobile Device | Web application only support one country but mobile is allowed to access multiple countries. | Functional | https://prnt.sc/8TU4FFMTxz89 | Not fixed
Bug_23 |  | Mobile Device | Some fields are not available on mobile app which is available on web. | Functional |  | Not fixed
Bug_24 | Login |  | After entering the password, this is showing double icon on view icon. | UI | https://prnt.sc/F9oK4_7UTMF4 | Fixed
Bug_25 | Password Recovery |  | Alignment of the fields need to fix. | UI | https://prnt.sc/qfBWFYAXJhte | Not fixed
Bug_26 |  |  | After submit the form, message and continue button is overlapping. | UI | https://prnt.sc/GsgnYPHUdVoI | Not fixed
Bug_27 | Header |  | Go to landing page is redirecting to othe URL. If it is managing on other url, it should open in new tab. | Functional | https://www.screencast.com/t/SYwusSJf | Fixed
Bug_28 | Search |  | Need to customize the alert similar like theme . | UI | https://prnt.sc/aPi4CuwtjSBb | no need to change as discussed
Bug_29 |  |  | Auto suggestive result alignment need to fix. | UI | https://prnt.sc/VfLnndTpDT5x | Not fixed
Bug_30 | Product Listing |  | Back button is not required on listing page. Breadcrumb is already there to redirect back. | UI | https://prnt.sc/psTtbSbC4vQW | Not required
Bug_31 |  |  | Double time page name is available | UI | https://prnt.sc/TWAwO_BcJ__6 | Fixed
Bug_32 | Product Details |  | Remove the Back button | UI | https://prnt.sc/7lHQHJHrWU0l | Not required
Bug_33 |  |  | Change the category name with breadcrumb and show the same top of the Title | UI | https://prnt.sc/2h8s92DErXxW | Not fixed
Bug_34 |  |  | Icon is missing for Packaging | UI | https://prnt.sc/CSdHtAp3jMcq | Not fixed
Bug_35 |  |  | Add to wishlist is disabled on listing page but same is not disabled on details page | Functional | https://www.screencast.com/t/SYwusSJf | Fixed
Bug_36 |  |  | Availability need to little bit right aligned and font size need to reduce | UI | https://prnt.sc/m7pEAEJUQZct | Fixed
Bug_37 |  | Mobile Device | Product name is cutting from left side | UI |  | Fixed
Bug_38 | My Profile |  | Contact number allow me to enter the text value | UI | https://prnt.sc/2yzAH0k-3fa5 | Fixed
Bug_39 |  | Mobile Device | Fields alignment need to fix | UI | https://prnt.sc/INs8wxThyJ9N | Not fixed
Bug_40 | Address | Add Address | Add address option is missing | UI | https://prnt.sc/AhYA8ZF7J6oK | Not fixed
Bug_41 |  | Edit Address | Validation messages on application is center aligned but here it is showing right aligned | UI | https://prnt.sc/6JFHlKb152K4 | Not fixed
Bug_42 |  | Edit Address | Mobile number should only allow to enter numeric value | UI | https://prnt.sc/0XCanmvTRKxU | Not fixed
Bug_43 |  | Edit Address | Fields need to align properly on mobile devices | UI | https://prnt.sc/f6Cg1I6Tz5e9 | Not fixed
Bug_44 |  | Delete | Need to customize the alert similar like theme . | UI | https://prnt.sc/jueDSlIU8Jv2 | no need to change
Bug_45 |  |  | Change Are you sure message to "Are you sure, you want to delete" | UI |  | Fixed
Bug_46 | Picture |  | If user try to click on upload button without uploading the picture. It should show the validation message | Functional | https://www.screencast.com/t/pJhQiVB1AZFA | Not fixed
Bug_47 |  | Mobile Device | Center aligned the choose option like upload button | UI | https://prnt.sc/bdX6-8SMiPtG | Not fixed
Bug_48 |  | Mobile Device | Increase the size of choose file | UI | https://prnt.sc/bdX6-8SMiPtG | Not fixed
Bug_49 | Change Password | Mobile Device | View icon need to show under the field | UI | https://prnt.sc/BVp9tYyLPo0y | Not fixed
Bug_50 |  |  | Change Password button need to be center aligned and reduce the space between field and button | UI | https://prnt.sc/wHMN18B6X6Rn | this is according to design
Bug_51 |  |  | While entering the data, view icon has been overlapping with other icon | UI | https://prnt.sc/L4zLYcz5i1Yh | Fixed
Bug_52 |  |  | Validation message need to align like other messages | UI | https://prnt.sc/saijnrjwyOBf | Fixed
Bug_53 |  |  | It should not remove the data from fields when old password is wrong | UI | https://prnt.sc/RWq3zzE7cJ1w | according to functionality it will remove the data if old password is wrong
Bug_54 |  |  | Old Password does not match message need to show the below of old password field | UI | https://prnt.sc/0YzBLSXgEWQr | Fixed
Bug_55 | Home | Recipe | Images are not showing | UI |  | Not fixed

## Client points for B2C
S.No. | Points | Comments | Bug/CR/Task | Hours Estimation if CR, Task | Tmotions comment in case of CR, Task | QA comment | QA Sign-Off | Manager Sign-Off | UAT Deployment | Client Sign-off | Other comments by Client
1 | In the registration page, for the nationality field, only “United Arab Emirates” option is there in the drop-down. |  | Task |  | Will do it. | Not fixed
2 | In the Delivery Address section, on the city field, only “Dubai” option is there. Keep it as a manual field. |  | Task |  | Will do it. | Not fixed
3 | The Snapchat icon is linked to the Instagram account, please link it to https://www.snapchat.com/add/chefmiddleeast. The Instagram icon is linked to the wrong profile, please link it to https://instagram.com/chefmiddleeastofficial?igshid=YmMyMTA2M2Y= . | Done | Bug |  |  | Fixed
4 | The categories shown in the category block are not as per B2C categorization. We have already shared the B2C category list. Also, the category block should be linked to the category product pages. The categories briefs are different for B2B & B2C. We have already shared the brief for both B2B & B2C. Please update accordingly. | We will do it | Task |  | Will do it. | Fixed
5 | Instead of so many social icons, it will be better to add one share icon. |  |  |  | CR we will do in support & maintenance | NA
6 | In the footer, instead of “Chef Middle East” make it “Chef Middle East at Home”. |  | Task |  | We will do it | Fixed
7 | There is no option to add new address on the My Account>>Profile>>Address Page |  | Bug |  | We will do it | Not fixed
8 | Maintain the design consistency on the product detail page. |  | Bug |  | We will do it | Fixed
9 | The home page banner is quite small to get the focus on the mobile devices. Is there any possibility to increase the height of the banner. |  |  |  | We will do it | not able to increase banner size as image is of that size,If I will increase the size,the image pixels got disturbed.
10 | On the register page, after filling all the fields when we click on the Register button. It gives an error message. |  |  |  | We will do it | Unable to check as wrong phone number message is showing https://prnt.sc/W8_Apui393IC
11 | All the fields should follow the same design on the registration page (rectangular or curved rectangle box). |  |  |  | We will do it | Fixed

## Client points for B2B
S.No. | Points | Comments |  | Bug/CR | Hours Estimation if CR | Tmotions comment in case of CR | QA comment | QA Sign-Off | Manager Sign-Off | UAT Deployment | Client Sign-off | Other comments by Client
1 | Catalogue uploaded doesn’t follow the order display sequence. | Done
2 | The images shown on the category pages are of different sizes. The images on the Chef's Larder and Meat & Poultry are not showing. Please share the correct size. So, we can provide the images accordingly. | We will do it please share images of Size 650 × 509 px
3 | When clicked on New & Event in the footer section, the page layout is changed. The News & Event in the main menu has different layout. | Done
4 | All the regions contact details are not showing on the mobile devices. | Done
5 | Remove the Comment (0) from the blog block on the New & Event Page on the mobile device. | Done
6 | When clicked on the contact us in the footer it gives an error message. | Done
7 | Align the category blocks on the home page, as it looks odd now. | Earlier there were 8 categories but now there are only 7 & the layout is same but we can change the layout in support & mainetenance | Cannot do need to plan new design layout we can pick in support & Maintenance
8 | Need to change the contact us email id on the Meat & Poultry and Chef's Larder. We will share the correct email id. | We will do it please share the correct ID
10 | Catalogue uploaded gives an error message when tried to download. | We will do it
11 | The category pages are not there on the main Menu Navigation | CR of 4 hours but we will do it
12 | "Who we are" section to be moved above the category section. | CR of 1 hour but we will do it
13 | Need to have the H1 tags on the home page for the SEO. | CR of 2 hours but we will do it
14 | Add space under the Read More button under the blog block on the home page. | Done